## Detail Civil (hidden)
DETAILED MEASUREMENT
NAME OF WORK : SETTING UP OF BURNS UNIT AT GOVT. MEDICAL COLLEGE, CALICUT
Item No. | Description of Item | No | Length | Width | Height | Quantity | Unit
SUB HEAD I : DISMANTLING AND DEMOLISHING
1 | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | [11 empty] | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge | Demolishing brick work manually /mechanical means including stacking of servicable material and disposal of unserviceable material within 50 metres lead as per direction of Engineer in charge
| Brick Walls between OT and Ward | 1 | 6 | 0.23 | 4 | 5.52
| Brick Walls toilets | 1 | 3 | 0.12 | 4 | 1.44
| Brick Walls | 1 | 0.75 | 0.23 | 4 | 0.69
| Sub total |  |  |  |  | 7.65 | Cum
2 | Dismantling windows and clerestory windows (steel or wood) including shutters chowkhats, architrave, holdfasts etc. complete and stacking with in 50m lead of area 3sq.meters and below. |  |  |  |  | 11 | E
3 | Dismantling Doors including shutters chowkhats, architrave, holdfasts etc. complete and stacking with in 50m lead of area below 3sq.meters |  |  |  |  | 6 | E
4 | Removing dry or oil bound distember ,water proofing cement paint and the like by scrapping,sand papering and preparing the surfacesmooth including necessary repairs to scratches etc complete. |  |  |  |  | 150 | Sqm
5 | Dismantling old plaster or skirting raking out joints and cleaning the surface for plaster including disposal of rubbish to the dumping ground within 50 metres lead. |  |  |  |  | 71 | Sqm | 15.56 | Rs .15
6 | Chipping dadoing/ Mosaic flooring laid in cement mortar including stacking of serviceable materials and disposal of unserviceable material within 50 metre lead |  |  |  |  | 200 | Sqm | LMR | 50
7 | Dismantling PVC pipe laid drainage line (of dia 110 mm or below) including disposal to dumping ground within 50 metre lead |  |  |  |  | 60 | Rm
8 | Dismantling of flushing cistern of all types (C.I./PVC/Vitrious China) including stacking of useful materials near the site and disposal of unserviceable materials within 50 metres lead. |  |  |  |  | 4 | E | 15.52 | 261.9
9 | Demolishing R.C.C. work manually/ by mechanical means including stacking of steel bars and disposal of unserviceable material within 50 metres lead as per direction of Engineer - in- charge. |  |  |  |  | 2 | Cum
SUB HEAD II : REINFORCED CEMENT CONCRETE
10 | Reinforced cement concrete work in beams, suspended floors, roofs having slope up to 15° landings, balconies, shelves, chajjas, lintels, bands, plain window sills, staircases and spiral stair cases up to floor five level, excluding the cost of centering, shuttering, finishing and reinforcement, with 1:1.5:3 (1 cement : 1.5 coarse sand : 3 graded stone aggregate 20 mm nominal size)
| Lintels | 1 | 2 | 0.23 | 0.2 | 0.092
| Lintels | 3 | 1.5 | 0.23 | 0.2 | 0.207
| Counter Slab | 1 | 5 | 0.6 |  | 3
| Sub Total |  |  |  |  | 3.299 | Sqm
11 | Centering and shuttering including strutting, propping etc. and removal of form for
| Lintels,beams. | 1 | 2 | 0.63 |  | 1.26
| Lintels | 1 | 1.5 | 0.63 |  | 0.945
| Counter Slab | 1 | 5 | 0.6 |  | 3
| Sub Total |  |  |  |  | 5.205 | Sqm
12 | Reinforcement for RCC works including straightening,cutting, bending, placing in position and binding all complete.
| Thermo Mechanically Treated Bars. | 3.299 | 120 |  |  | 395.88 | Kg
SUBHEAD III: BRICK WORK
13 | Brick work in cement mortar 1:6 (1 cement : 6 coarse sand) using first class Wire cut bricks ( 22.9 x 11.20 x 7.0 cm) outer exposed and inside with country burnt bricks for superstructure including scaffolding, raking out the joints, curing, cost and conveyance of all materials, labour, lead, lift etc.complete (4'')
| Brick Walls - | 1 | 3 |  | 4 | 12
| Sub Total |  |  |  |  | 12 | Sqm
14 | Extra for providing and placing in position 2 nos of 6 mm dia M.S bars at every third course of half brick masonry. | 12 |  |  |  | 12 | Sqm
SUB HEAD IV: ALUMINIUM WORK
15 | Providing and fixing aluminium work for doors, windows, ventilators and partitions withextruded built up standard tubular sections/ appropriate Z sections and other sections ofapproved make conforming to IS: 733 and IS: 1285, fixing with dash fasteners of required dia and size, including necessary filling up the gaps at junctions, i.e. at top, bottom and sides with required EPDM rubber/ neoprene gasket etc. Aluminium sections shall be smooth, rust free, straight, mitred and jointed mechanically wherever required including cleat angle, Aluminium snap beading for glazing / paneling, C.P. brass / stainless steel screws, all complete as per architectural drawings and the directions of Engineer-in-charge. (Glazing, paneling and dash fasteners to be paid for separately) : a) For fixed portion . Powder coated aluminium (minimum thickness of powder coating 50 micron) of required colour as directed by the engineer in charge.
| Ventilators (120x0.60) | 2 | 3.6 |  |  | 7.2 | Rm | 13 | 1.5 | 1.2 | 23.4
| Doors(230 x220) | 1 | 6.7 |  |  | 6.7 |  | 2 | 2.3 | 2.2 | 10.12
| Door (90 x220) | 2 | 6.2 |  |  | 12.4
| Sub Total |  |  |  |  | 26.3 | Rm |  |  |  | 33.52 | 301.68
[6 empty] | 118.613 | Kg |  | 2802
16 | For shutters of doors, windows & ventilators including providing and fixing hinges/ pivots and making provision for fixing of fittings wherever required including the cost of EPDM rubber / neoprene gasket required (Fittings shall be paid for separately) Powder coated aluminium (minimum thickness of powder coating 50 micron) of required colour as directed by the engineer in charge.
| Ventilators (120x0.60) | 2 | 1.2 |  | 0.6 | 1.44
| Doors(230 x220) | 1 | 2.3 |  | 2.2 | 5.06
| Doors(90 x220) | 6 | 0.9 |  | 2.2 | 11.88
| Partition for Nurses Room | 2 | 2.4 |  | 2.1 | 10.08
| Partition for Nurses Room | 2 | 2.1 |  | 2.1 | 8.82
| Sub Total |  |  |  |  | 37.28 | Sqm
[6 empty] | 223.68 | Kg
17 | Providing and fixing 12 mm thick prelaminated particle board flat pressed three layer or graded wood particle board conforming to IS: 12823 Grade l Type ll, in panelling fixed in aluminum doors, windows shutters and partition frames with C.P. brass / stainless steel screws etc. complete as per architectural drawings and directions of engineer-in-charge. Pre-laminated particle board with decorative lamination on both sides
| Doors(0.90 x220) | 6 | 0.9 |  | 0.9 | 4.86
| Sub Total |  |  |  |  | 4.86 | Sqm
18 | Providing and fixing glazing in aluminium door, window, ventilator shutters and partitions etc. with EPDM rubber / neoprene gasket etc. complete as per the architectural drawings and the directions of engineer-in-charge . (Cost of aluminium snap beading shall be paid in basic item): With float glass panes of 5.50 mm thickness
| Ventilators (120 x60) | 2 | 1.2 |  | 0.6 | 1.44
| Doors (90 x 220) | 6 | 0.9 |  | 1.3 | 7.02
| Doors(230 x220) | 1 | 2.3 |  | 2.2 | 5.06
| Sub Total |  |  |  |  | 13.52 | Sqm
19 | Providing and fixing double action hydraulic floor spring of approved brand and manufacture IS : 6315 marked, DORMA make or equivalent for doors including cost of cutting floors as required, embedding in floors and cover plates with brass pivot and single piece M.S. sheet outer box with slide plate etc. complete as per the direction of Engineer-in-charge With Stainless Steel cover plate |  |  |  |  | 5 | Each
20 | Providing and fixing aluminium handles ISI marked anodised ( anodic coating not less than grade AC 10 as per IS: 1868) transparent or dyed to required colour or shade with nuts and screws etc. complete-
| 125 mm |  |  |  |  | 4 | Each
| 100mm |  |  |  |  | 4 | Each
21 | Providing and fixing aluminium tower bolts ISI marked anodised ( anodic coating not less than grade AC 10 as per IS: 1868) transparent or dyed to required colour or shade with nuts and screws etc. complete-
| 250 X 10 mm |  |  |  |  | 4 | Each
| 150x10mm |  |  |  |  | 4 | Each
22 | Providing and fixing IS : 3564 marked aluminium extruded section body tubular type universal hydraulic door closer with double speed adjustment with necessary accessories and screws etc. complete. |  |  |  |  | 4 | Each
23 | Providing and fixing 100mm brass locks (best make of approved quality) for aluminium doors including necessary cutting and making good etc. complete. |  |  |  |  | 4 | Each
24 | Providing fixing aluminium casement windows fastener of required length for aluminium windows with necessary screws etc. complete. Powder coated minimum thickness 50 micron aluminium |  |  |  |  | 10 | Each
25 | Providing and fixing stainless steel (SS 304 grade) adjustable friction windows stays of approved quality with necessary stainless steel screws etc. to the side hung windows as per direction of Engineer- in-charge complete. 255 X 19 mm |  |  |  |  | 10 | Each
26 | Providing and fixing aluminium hanging floor door stopper, ISI marked, anodised (anodic coating not less than grade AC 10 as per IS : 1868) Transparent or dyed to required colour and shade, with necessary screws etc. complete. Twin rubber stopper |  |  |  |  | 8 | Each
SUB HEAD V: :STEEL WORK
27 | Providing and fixing M.S. grills of required pattern in frames of windows etc. with M.S. flats, square or round bars etc. including priming coat with approved steel primer all complete. Fixed to openings /wooden frames with rawl plugs screws etc
| Windows (120 x150 ) | 10 | 1.2 |  | 1.5 | 18 | Sqm
| Sub Total |  |  |  |  | 396 | Kg
SUB HEAD VI : PVC WORK.
28 | Providing and fixing factory made uPVC door frame made of uPVC extruded sections having an overall dimension as below (tolerance ±1mm), with wall thickness 2.0 mm (± 0.2 mm), corners of the door frame to be Jointed with galvanized brackets and stainless steel screws, joints mitred and Plastic welded. The hinge side vertical of the frames reinforced by galvanized M.S. tube of size 19 X 19 mm and 1mm (± 0.1 mm) wall thickness and 3 nos. stainless steel hinges fixed to the frame complete as per manufacturer’s specification and direction of Engineer-n-charge - Extruded section profile size 48x40 mm
| Toilets | 2 | 5.9 |  |  | 11.8 | Rm
29 | Providing and Fixing 30 mm thick factory made Polyvinyl Chloride (PVC) door shutter made of styles and rails of a uPVC hollow section of size 60x30 mm and wall thickness 2 mm (± 0.2 mm), with inbuilt decorative moulding edging on one side. The styles and rails mitred and joint at the corners by means of M.S. galvanised/ plastic brackets of size 75x220 mm having wall thickness 1.0 mm and stainless steel screws. The styles of the shutter reinforced by inserting galvanised M.S. tube of size 25x20 mm and 1 mm (± 0.1 mm) wall thickness. The lock rail made up of 'H' section, a uPVC hollow section of size 100x30 mm and 2 mm (± 0.2 mm) wall thickness fixed to the shutter styles by means of plastic/ galvanised M.S. 'U' cleats. The shutter frame filled with a uPVC multi-chambered single panel of size not less than 620 mm, having over all thickness of 20 mm and 1 mm (± 0.1 mm) wall thickness . The panels filled vertically and tie bar at two places by inserting horizontally 6 mm galvanised M.S. rod and fastened with nuts and washers, complete as per manufacturer's specification and direction of Engineer-in-charge.
| Toilets | 2 | 0.75 |  | 2.2 | 3.3 | Sqm
SUB HEAD VII : WATER PROOFING.
30 | Providing and application of bituminous water proof protective coating confirming to IS 9862-1981 Fosroc Nitoproof 100/120 over cleaned and well prepared surface(vertical/horizontal) with a priming coat of Nitoproof 100 over with two coats of Nitoproof 120strictly following the manufactures specification and application procedure, including necessary chipping and refilling of construction joints with cement mortar 1:4 added with Nitobond SBR@ 2 lit per bag of cement and pressure grouting of weaker area, construction joints and honey combs if any with cement slurry mixed with plasticized expanding additive cebex 100 including cost of labour tools etc but excluding scaffolding , cement and sand complete etc or equivalent.
| Toilets | 2 | 3.85 |  | 2.9 | 22.33
| Sub Total |  |  |  |  | 22.33 | Sqm
SUB HEAD VIII : FLOORING
31 | Providing and laying Ceramic joint free antiskid floor tiles of size 400x400 mm thicknes 7.5mm of 1st quality conforming to IS : 15622, of JOHNSON, NITCO, ORIENT, KAJARIA or approved make, in all colours, shades, except White, Ivory, Grey, Fume Red Brown, laid on 20 mm thick bed of cement mortar 1:4 (1 Cement : 4 Coarse sand), including pointing the joints with white cement and matching pigments etc:- complete.
| Toilets | 2 | 3.85 | 2.9 |  | 22.33
| Sub Total |  |  |  |  | 22.33 | Sqm
32 | Providing and fixing Ist quality ceramic glazed wall tiles conforming to IS:15622(thickness to be specified by the manufacture) of approved make in all colours, shades except burgundy, bottle green, black of any size as approved by Engineer-in-Charge in skirting, risers of steps and dados over 12mm thick bed of cement mortar 1:3 (1 cement : 3 coarse sand) and jointing with grey cement slurry @ 3.3kg per sqm including pointing in white cement mixed with pigment of matching shade complete. | [5 empty] | sqm
| Toilets | 4 | 2.9 |  | 2.3 | 26.68
| Toilets | 4 | 3.82 |  | 2.3 | 35.144
| Icu /ward | 1 | 27.1 |  | 2.3 | 62.33
| Icu /ward | 1 | 26.2 |  | 2.3 | 60.26
| Lobby | 1 | 10 |  | 2.3 | 23
Deduct
| Windows (120 x150 ) | -4 | 1.2 |  | 1.5 | -7.2
| Sub Total |  |  |  |  | 200.214 | Sqm
33 | Providing and laying Vitrified floor tiles of Size1000 x 1000 mm, thickness of 10mm or nearest size with water absorption less than 0.08% and conforming to IS : 15622, of approved make, with 3 mm spacers and filled with color grout finished with required slope and level,curing,rubbing,cleaning etc, in all colours and shades and design as per the drawing, laid on fixing glazed/ Ceramic/ Vitrified floor tiles with cement based high polymer modified quick-set tile adhesive (Water based) conforming to IS: 15477, in average 3mm thickness. including grouting the joints with white cement and matching pigments etc., complete. as directed by the Engineer in charge. ( Basic price of Tile not less than Rs. 1500 per sqm)
| ICU/WARD | 1 | 7.6 | 6.2 |  | 47.12
| ICU/WARD | 1 | 7.3 | 6.2 |  | 45.26
| Corridor | 1 | 3.2 | 2.3 |  | 7.36
| Sub Total |  |  |  |  | 99.74 | Sqm
SUB HEAD IX : FINISHING.
34 | Plastering in cm 1:3, 12 mm thick floated hard and trowelled smooth including watering ,curing cost and conveyance of all materials and labour charges etc complete with water proofing compound.
Inside Walls
| Toilets | 1 | 2.9 |  | 0.8 | 2.32
| Toilets | 2 | 6 |  | 0.8 | 9.6
| ICU / Ward | 2 | 7.4 |  | 0.8 | 11.84
| ICU / Ward | 2 | 7.1 |  | 0.8 | 11.36
| ICU / Ward | 4 | 6 |  | 0.8 | 19.2
| Sub Total |  |  |  |  | 54.32 | Sqm
35 | 15 mm cement plaster on the rough side of single or half brick wall ( 1:4)
| Toilet | 2 | 3.82 |  | 0.8 | 6.112
| Toilet | 2 | 2.9 |  | 0.8 | 4.64
| Sub Total |  |  |  |  | 10.752 | Sqm
36 | Wall painting with acrylic emulsion paint of approved brand and manufacture to give an even shade : Two or more coats on new work .
Ceiling
| Toilets/ Corridor | 1 | 6 | 2.9 |  | 17.4
| Icu/ Ward | 1 | 7.4 | 6 |  | 44.4
| Icu/ Ward | 1 | 7.1 | 6 |  | 42.6
| Sub Total |  |  |  |  | 104.4 | Sqm
Inside Walls
| Toilets | 4 | 2.9 |  | 0.8 | 9.28
| Toilets | 4 | 3.82 |  | 0.8 | 12.224
| Icu /ward | 1 | 27.1 |  | 0.8 | 21.68
| Icu /ward | 1 | 26.2 |  | 0.8 | 20.96
| Lobby | 1 | 10 |  | 0.8 | 8
| Deduct |  |  |  |  | 0
| Windows (120 x150 ) | -4 | 1.2 |  | 1.5 | -7.2
| Sub Total |  |  |  |  | 64.944 | Sqm
| Total |  |  |  |  | 169.344 | Sqm
36 | Painting with synthetic enamel paint of approved brand and manufacture of required colour to give an even shade :Two or more coats on new work over an under coat of suitable shade with ordinary paint of approved brand and manufacture. |  |  |  |  | 18 | Sqm
SUB HEAD X : ROOFING
37 | Providing and fixing suspended acoustic mineral fibre ceiling with 15mm grid with 4mm GI rod with 6mm nylon rawl plug and butterfly clips at every 1220mm intervals at the main T and laying of approved microlook ceiling panels with 12-15mm tiles NRC-.0.5,STC value -35, Light reflection 85 %,humidity resistance RH 95 % with tegular edge.ARMSTRONG /DAIKEN/NITTOBO or approved equivalent make. The rate include making cut out openings with additional frame work wherever required for eletrical fixtures,grills,diffusers & access panels etc. complete
Inside Walls
| Ward / Icu | 1 | 7.1 | 6 |  | 42.6
| Ward / Icu | 1 | 7.4 | 6 |  | 44.4
| Lobby | 1 | 2.9 | 2.1 |  | 6.09
| Sub Total |  |  |  |  | 93.09 | Sqm
SUB HEAD XI : SANITARY INSTALLATIONS & WATER SUPPLY
38 | Supply and fixing wall hanging type water closet with flushing cistern('HIND WARE'/' CERA' (special colours) or equivalent), with seat cover, along with all necessary requirement for fixing etc. complete. |  |  |  |  | 2 | E
39 | Providing and fixing wash basin with C.I. brackets, 15 mm C.P. brass pillar taps, 32 mm C.P. brass waste of standard pattern, including painting of fittings and brackets, cutting and making good the walls wherever require White Vitreous China Flat back wash basin size 550x 400 mm with single 15 mm C.P. brass pillar tap |  |  |  |  | 2 | E
40 | Providing and fixing white vitreous china flat back or wall corner type lipped front urinal basin of 430x260x350 mm and 340x410x265 mm sizes respectively with automatic flushing cistern with standard flush pipe and C.P. brass spreaders with brass unions and G.I clamps complete, including painting of fittings and brackets, cutting and making good the walls and floors wherever required : One urinal basin with 5 litre white P.V.C. automatic flushing cistern |  |  |  |  | 2 | E
41 | Providing and fixing P.V.C waste pipe for sink or wash basin, including P.V.C waste fittings complete :-
| Flexible pipe :-32 mm dia. |  |  |  |  | 2 | E
42 | Providing and fixing trap of self cleansing design with screwed down or hinged grating with or without vent arm complete, including cost of cutting and making good the walls and floors
| a)100mm inlet and 75mm outlet. |  |  |  |  | 2 | E
43 | Providing and jointing PVC pipes of (Pressure10 K g/cm2) for water supply including testing of joints, concealing the pipes , & trenching & refilling wherever required etc complete.
| 20mm PVC pipe |  |  |  |  | 25 | M
| 25mm PVC pipe |  |  |  |  | 25 | M
| 32mm PVC pipe |  |  |  |  | 25 | M
| 40mm PVC pipe |  |  |  |  | 25 | M
44 | Providing and fixing PTMT grating of approved quality and colour. 150 mm nominal size square 100 mm diameter of the inner hinged round grating |  |  |  |  | 5 | E
45 | Providing and fixing C.P. brass long body bib cock of approved quality conforming to IS standards and weighing not less than 690 gms. 15mm nominal bore |  |  |  |  | 5 | E
46 | Providing and fixing unplasticised rigid P.V.C pipe conforming to IS Standards(Pressure 6kg/cm2) in drainage lines including cutting and making good the walls,cutting and refilling of earth, jointing all etc complete | [5 empty] | E
| 110mm dia |  |  |  |  | 40 | m
| 75mm dia |  |  |  |  | 25 | m | 0.1125
47 | Providing & fixing PVC Fittings and fixtures Conforming IS specifications including cutting and making good the walls etc complete | [6 empty] | 4.95
| 110mm dia plain elbow |  |  |  |  | 30 | E | 1.63
| 75mm dia plain elbow |  |  |  |  | 30 | E | 3.3
| 110mm dia door elbow |  |  |  |  | 30 | E | 9.88
| 75mm dia door elbow |  |  |  |  | 30 | E
| 110mm dia plain bend |  |  |  |  | 30 | E
| 75mm dia plain bend |  |  |  |  | 30 | E
| 110mm dia door tee |  |  |  |  | 20 | E
| 75mm dia door tee |  |  |  |  | 20 | E
| 110mm dia air cowl |  |  |  |  | 20 | E
| 75mm dia air cowl |  |  |  |  | 20 | E
| 110mm dia offset |  |  |  |  | 20 | E
| 75mm dia offset |  |  |  |  | 20 | E
48 | Providing and fixing C.P. brass bib cock of approved qualityconforming to IS:8931. 15mm nominal bore |  |  |  |  | 10 | E |  |  |  | 2.58
49 | Providing and fixing C.P. brass stop cock (concealed) of standard design and of approved make conforming to IS:8931. 15mm nominal bore |  |  |  |  | 10 | E
50 | Providing and fixing unplasticised P.V.C connection pipe with brass unions :- 45 cm length | [5 empty] | E
| 15MM nominal bore |  |  |  |  | 10 | E
51 | Providing and fixing gun metal gate valve with CI wheel of approved quality (screwed end) – | [5 empty] | E
| 32 mm dia nominal bore |  |  |  |  | 10 | E
52 | Providing and fixing ball valve (brass) of approved quality complete. High or low pressure with plastic floats 25 mm nominal bore |  |  |  |  | 10
66
2.58
2.58
2.58
2.58
0
2.58
0
0
#VALUE!
2.58
0
2.58
[10 empty] | 16.68 | 536.65
2.58
2.58
0
0
0
0
0
2.58
0
0
2.58
#VALUE!
0
2.58
0
2.58
0
2.58
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
2.58
2.58
2.58
2.58
2.58
2.58
2.58
6743.55
171
171
2
4*25
11*2
4*4
585.8232
1007.552
5046.8

## Electrical
SETTING UP OF BURNS UNIT AT GOVT: MEDICAL COLLEGE, KOZHIKKODE
PART B -ELECTRICAL WORKS
Sl No | Description of Items | Unit | Qty | Rate Rs infigures & words) | Amount in Rs
A | Wiring
1 | Wiring for light point / fan point / exhaust fan point / call bell point with 1.5 sq.mm FR PVC insulated copper conductor single core cable in surface/recessed PVC conduit with modular switch, modular plate, suitable GI box and earthing the point with 1.5 sqmm, FR PVC insulated copper conductor single core cable etc. as required.
| Group B | Point | 40
2 | Wiring for circuit/submain wiring along with earth wire with the following sizes of FR PVC insulated copper conductor, single core cable in surface/recessed PVC conduit as required.
a | 2 x 1.5 sqmm + 1.5 sqmm earth wire | Rm | 120
b | 2 x 2.5 sqmm + 2.5 sqmm earth wire | Rm | 300
c | 2 x 4 sq. mm + 1 x 4 sq. mm earth wire | Rm | 60
d | 2 x 6 sq. mm + 1 x 6 sq. mm earth wire | Rm | 60
3 | Telephone wiring in existing conduit : Supplying and drawing following pair 0.5 sq.mm FR PVC insulated copper conductor,unarmored telephone cable in the existing surface/recessed PVC conduit as required
a | 2 Pair | Rm | 120
b | 4 Pair | Rm | 60
4 | Supplying and fixing of following sizes of PVC conduit along with the accessories in surface/ recess including painting in case of surface conduit , or cutting the wall and making good the same in case of recessed conduit as required for wiring.
a | 20mm | Rm | 150
b | 25mm | Rm | 60
5 | Supplying and fixing following modular switch/socket on the existing modular plate & switch box including connections but excluding modular plate etc. as required.
| Telephone socket outlet | Each | 2
6 | Supplying and fixing stepped type electronic fan regulator on existing modular plate switch box including connections but excluding modular plate etc.as required. | nos | 2
7 | Supplying and fixing modular blanking plate on the existing modular plate & switch box excluding modular plate as required. | Each | 20
8 | Supplying and fixing following size/ modules, GI box alongwith modular base & cover plate for modular switches in recess etc as required.
| 1 or 2 Module (75mmX75mm) | Each | 5
9 | Supplying and fixing suitable size GI box with modular plate and cover in front on surface or in recess including providing and fixing 3 pin 5/6 amps modular socket outlet and 5/6 amps modular switch, connection, painting etc. as required | Each | 35
10 | Supplying and fixing suitable size GI box with modular plate and cover in front on surface or in recess including providing and fixing 6 pin 15/16 & 5/6 amps modular socket outlet and 15/16 amps modular switch, connection, painting etc. as required | Each | 20
11 | Installation, testing and commissioning of pre-wired, fluorescent fitting / compact fluorescent fitting of all types, complete with all accessories and tube etc. directly on ceiling/ wall, including connection with 1.5 sq. mm FR PVC insulated, copper conductor, single core cable and earthing etc. as required. | Each | 10
12 | Installation of exhaust fan in the existing opening, including making good the damage, connection, testing, commissioning etc. as required.
| Upto 450 mm sweep | Each | 2
13 | Installation, testing and commissioning of ceiling fan, including wiring the down rods of standard length (upto 30 cm) with 1.5 sq. mm FR PVC insulated, copper conductor, single core cable etc. as required. | Each | 2
14 | Supplying and fixing extra down rod of 10 cm length G.I. pipe ,15 mm dia, heavy gauge including painting etc. as required. (Note : More than 5 cm length shall be rounded to the nearest 10 cm and 5 cm or less shall be ignored) | Each | 10
15 | Supplying and fixing following way prewired SP&N MCB distribution board of steel sheet for 240 volts on surface/ recess complete with loose wire box, terminal connectors for all incoming and outgoing circuits, duly prewired with suitable size FR PVC insulated copper conductor up to terminal blocks, tinned copper bus bar, neutral link, earth bar, din bar, detachable gland plate, interconnections, powder painted including earthing etc. as required. (But without MCB/ RCCB/ Isolator)
| 12 way, Double door | Each | 2
16 | Supplying and fixing following way prewired vertical type TP&N MCB distribution board of steel sheet for 415 volts on surface/ recess complete with loose wire box of sheet steel, dust protected, duly powder painted, inclusive of 200 amps tinned copper bus bar, common neutral link, earth bar, din bar for mounting MCB's, terminal connectors for all incoming and outgoing circuits, duly prewired with adequate size of FR PVC insulated copper conductor upto the terminal connector/ neutral link, earthing etc as required (But without MCB/ RCCB/ Isolator). (Note : Prewired vertical type MCB TPDB is normally used where 3 phase outlets are required.)
| 6 way, Double door | Each | 2
17 | Supplying and fixing following way prewired TP&N MCB distribution board of steel sheet for 415 volts on surface/ recess complete with loose wire box, terminal connectors for all incoming and outgoing circuits, duly prewired with suitable size FR PVC insulated copper conductor up to terminal blocks, tinned copper bus bar, neutral link, earth bar, din bar, detachable gland plate, interconnections, powder painted including earthing etc. as required.(But without MCB/ RCCB/ Isolator)
a | 4 way, Double door | Each | 1
b | 6 way, Double door | Each | 1
18 | Supplying and fixing 5 amps to 32 amps rating, 240 volts `B' curve, miniature circuit breaker suitable for lighting and other loads of following poles in the exisiting MCB DB complete with connections,m testing and commissioning etc, as required.
a | Single pole | Each | 40
b | Double pole | Each | 2
c | Triple pole | Each | 5
d | Triple pole and neutral | Each | 2
19 | Supplying and fixing single pole blanking plate in the existing MCB DB complete etc. as required. | Each | 20
20 | Supplying and fixing following rating, double pole, 240 volts, isolator in the existing MCB DB complete with connections, testing and commissioning etc. as required.
| 40 amps | Each | 1
21 | Supplying and fixing following rating, double pole, (single phase and neutral), 240 volts, residual current circuit breaker (RCCB), having a sensitivity current upto 300 milliamperes in the existing MCB DB complete with connections, testing and commissioning etc. as required.
| 40 amps | Each | 1
22 | Supplying and fixing following rating, four pole, 415 volts, isolator in the existing MCB DB complete with connections, testing and commissioning etc. as required.
a | 40 amps | Each | 2
b | 63 amps | Each | 1
23 | Supplying and fixing following rating, four pole, (three phase and neutral), 415 volts, residual current circuit breaker (RCCB), having a sensitivity current upto 300 milliamperes in the existing MCB DB complete with connections, testing and commissioning etc. as required.
a | 25 amps | Each | 1
b | 40 amps | Each | 2
c | 63 amps | Each | 1
24 | Supplying and fixing 20 amps, 240 volts, SPN industrial type, socket outlet, with 2 pole and earth, metal enclosed plug top alongwith 20 amps "C" curve, SP, MCB, in sheet steel enclosure, on surface or in recess, with chained metal cover for the socket out let and complete with connections, testing and commissioning etc. as required. | Each | 7
25 | Supplying and fixing DP sheet steel enclosure on surface/ recess along with 25/32amps 240 volts "C" curve DP MCB complete with connections, testing and commissioning etc. as required. | Each | 2
26 | Supplying and fixing TP sheet steel enclosure on surface/ recess along with 16/25/32amps 415 volts "C" curve TP MCB complete with connections, testing and commissioning etc. as required. | Each | 2
27 | Providing and fixing 6 SWG dia G.I. Wire on surface or in recess for loop earthing as required. | Rm | 200
28 | Supplying and making end termination with brass compression gland and aluminium lugs for following size of PVC insulated and PVC sheathed / XLPE aluminium conductor cable of 1.1 KV grade as required.
a | 3.5C x 35 sqmm | Each | 2
b | 4C x 16 sqmm | Each | 6
c | 4C x 10 sqmm | Each | 4
d | 4C x 6 sqmm | Each | 4
29 | Laying and fixing of one number PVC insulated and PVC sheathed / XLPE power cable of 1.1 kV grade of following size on wall surface as required.
| Upto 35 sq. mm (clamped with 1mm thick saddle) | Rm | 230
30 | Supply of following size 1.1 KV grade XLPE insulated, PVC sheathed, armoured Aluminium conductor power cable conforming to IS 7098 (Part 1) amended upto date.
a | 3.5C x 35 sqmm | Rm | 100
b | 4C x 16 sqmm | Rm | 50
c | 4C x 10 sqmm | Rm | 50
d | 4C x 6 sqmm | Rm | 30
31 | Supply of 1x28W, indoor surface mountable fluorescent CRCA sheet steel power coated body light fixture, 28W T5 lamp, electronic HPF ballast, lamp holder, prewired complete with all necessary accessories suitable for operation on 230V, 50Hz AC supply as required (Philips TMS122 M 2xTL5-28W EBT / Crompton T5GP28EB / Bajaj BTIR 128) | Each | 5
32 | Supply and installation of recess mounted type 2x36W CFL cleanroom light fitting with option of rear opening / front opening in robust CRCA housing, glass cover with all electrical accessories like electronic ballast, lamp holder, 36W CFL lamps, mounting chain, hook etc complete as required. (Philips FCS650 2xPL-L36W EBP FOP GT / Crompton CRFW12236EB / Bajaj BPRF 236C LHD) | Each | 18
33 | Supply and installation of indoor recess mounted LED down light fixture with die-cast reflector housing, high efficiency diffuser, LED lamp, constant current electronic driver, high efficiency white reflector, prewired complete with all necessary accessories suitable for operation on 230V, 50Hz AC supply as required (Philips BBS 181 1xDLED - 5000 PSU WH / Crompton LCDLH108G/WW-N / Bajaj BGSLO 12 1.2 WH). | Each | 10
34 | Supply of 1x18W surface mounted luminaire with opal acrylic diffuser complete with all electrical accessories like electronic ballast, lamp holder, 18W T8 lamps etc. complete with all mounting accessories etc as required. (Philips TMS520/ 118 / Crompton T5JB13114EB9) | Each | 3
35 | Supply of 1200 mm sweep min three star rated ceiling fan complete with motor, double ball bearing, blades, canopy, 30 cm down rod and without speed regulator suitable for 230 V 50 HZ, AC supply confirms to IS 374/1979 as required complete. (Make Usha Technix or Crompton High Breeze Plus or equivalent). | Each | 2
36 | Supply of medium duty exhaust fan 300 mm sweep, 900 rpm, metal blades of approved colour, for single phase 230 volt, 50Hz AC supply complete with motor, capacitor and all accessories as required complete. | Each | 2
37 | Supply and installation of 3 Wings , 400mm Sweep, Decorative Wall Mounted fan with cords for Control with all accessories similar to Usha Helix Hi speed or Equi. | Each | 2
38 | Supplying and fixing PVC batten / angle holder including 13W CFL lamp, connection etc as required. | Each | 5
39 | Supply, installation, testing & commissioning of 3 kVA, 1 phase input, 1 phase output, true on-line UPS system with 30 minutes back up (full load), including all accessories, SMF batteries VRLA type with powder coated MS cabinet, battery cabling including all accessories as required complete having following specification.
Fully digital controlled based on DSP
Power factor corrected from end > 0.9
Pure sine wave output.
Full time output voltage & frequency regulation
Auto regulation of battery end voltage
Intelligent interface with LED/LCD display
Static bypass switch & manual by pass switch
| Auto temperature compensation | Each | 1
40 | Supplying and fixing following rating, 415 volts, C curve MCB in the existing DB, enclosure complete with connections, testing and commissioning etc. as required.
a | 40A TP MCB | Each | 2
b | 63A TP MCB | Each | 1
41 | Supply and laying 4 pair CAT 6 UTP cable in the exisitng surface / recessed steel / PVC conduit as required. | Rm | 120
42 | Supply & fixing modular type computer outlet (RJ-45) with modular base and cover plate, GI box complete with all accessories, connection etc. complete as required. | Each | 2
43 | Supply and fixing of 10 pair MDF box, back mount frame and original krone connectors with all accessories. | Each | 1
44 | Supply, installation, testing and commissioning of Air Cooled High Wall mounted Split Air Conditioner of following capacity consisting of high wall mounted type room unit (fan coil) with cordless remote control and one number outdoor condensing unit comprising of enegy efficient suitable rotary compressor for operation on single phase, 230 V, 50Hz supply, fixing the outdoor unit on a raised platform as per manufacturers recommendation and fixing of room (fan coil) unit on wall, upto 10 m distance refrigerant copper piping with 13mm nitrile rubber insulation, providing and making interconnection between room & condenser as per site conditions, comprising of 1" dia drain PVC pipe with insulation 10m, canvas connections, full electrical cabling from power plug near indoor unit and to outdoor unit, vibration isolators, ODU MS Stand, first charge refrigarant gas, BEE energy rated with suitable stabilizer etc complete as required.
| 2 TR 4 star rated | nos | 5
45 | Supply and providing 6 mm thick & 1 m wide electrical grade chequered type rubber mat to withstand 3.3 KV dielectric strength conforming to IS 5429/ 1969. | Rm | 5
TOTAL PART B -ELECTRICAL WORKS
GRAND TOTAL - PART A + PART B